## Slide 1: NCHRP Project 10-113, “Quality Management for 3D Model-Based Project Development and Delivery”
Guide Overview
Image: HDR, used with permissions
Notes: Title slide. Suggested speaker notes
Welcome to today’s presentation: NCHRP Project 10-113, Quality Management for 3D Model-Based Project Development Delivery
Hello, my name is [ENTER YOUR NAME HERE]
I will be presenting an overview of the guide developed under this project
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 2: Research Team
Principal Investigator/Project Manager
Alexa Mitchell, PE (HDR)
Co-Principal Investigators | Project Support
Jennifer Steen, PE (HDR) Marcia Yockey, PE (HDR) Francesca Maier, PE (Fair Cape Consulting) Hala Nassereddine, PhD (KY Transportation Research Center) Rachel Catchings (KY Transportation Research Center) | John Reese – Digital Delivery Advisor (HDR) Colby Christensen, PE – Bridge Digital Delivery Lead (HDR) Dan Prokop, PE – Bridge Digital Delivery Lead (HDR) Dan Domalik, PE – Transportation Quality Manager (HDR) Chris VanDyke, PhD – Technical Editor (KY Transportation Research Center) Gisele DesRosiers – Graphic Designer (HDR)
Notes: Suggested speaker notes:
The research team was led by HDR in collaboration with Fair Cape Consulting, and the Kentucky Transportation Research Center
Table lists the names of the principal investigator, co-principal investigators and project support staff
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 3: Project Objectives
The objective of this research is to provide a guide to assist State DOTs with developing quality management processes for 3D model-based approach for project development and delivery
Notes: Suggested Speaker Notes:
The objective of this research is to provide a guide to assist State DOTs with developing quality management processes for 3D model-based approach for project development and delivery
The Guide serves as a national reference for quality management.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 4: Research Project Timeline
2020
Problem statement developed and submitted
2021
Funded, panel formed, issued RFP
2022
Awarded contract, research started September
2023
Interim Report 1, Agency testing, Interim Report 2 with guide outline
2024
Interim Report 3 with draft guide, workshops
2025
Guide, conduct of research report, webinar, outreach materials, implementation plan
Notes: Suggested Speaker Notes
The Research Project Timeline extended over 6 years.
2020 – Problem statement developed
2021 – Project funded, panel formed, RPF issued
2022 – Awarded contract to research team
2023 – Interim reports, agency testing
2024 – Draft guide submitted; initial workshops conducted
2025 – Final deliverables submitted
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 5: Agenda
Guide Introduction
Quality Management Concepts
3D Model Reviews
Setting up for Success
Sample Quality Artifacts
Implementation
Notes: Suggested Speaker Notes
The agenda for today’s presentation includes
Guide Introduction
Quality Management Concepts
3D model Reviews
Setting up for Success
Sample Quality Artifacts
Implementation
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 6: Guide Introduction
Notes: Suggested Speaker Notes
This section will be about the Guide Introduction
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 7: Objectives of the Guide
Provide guidance for implementing the quality process for:
  3D model-based design review
  3D model-based deliverable review
  data validation, and
  paperless documentation procedures
Notes: Suggested Speaker Notes
The objectives of the guide will provide guidance for implementing the quality process for the following aspects
3D model based design reviews
3D model based deliverable reviews
Data validation
Paperless documentation procedures
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 8: Managing Expectations
This Guide Is
Guidance on how to update your quality program for digital delivery
A holistic view of how the use of digital media (including 3D models) affects the quality process
Pragmatic suggestions for current technology constraints and forward-looking
Augmented by real-world examples in the appendices
This Guide Is NOT
Materials that can be directly inserted into your quality program
A checklist that addresses all concerns
Notes: Suggested Speaker Notes
This guide IS
Guidance on how to update an agency quality program for digital delivery
Holistic view of how digital media affects the quality process
Pragmatic suggestions for current and future technology constraints
Augmented with real world examples in the appendices
This guide is NOT
Materials that can be directly inserted into a program
A complex checklist that addresses all concerns for a review
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 9: Gaps
PEOPLE
Undefined skillsets
Lack of capacity
PROCESS
Out of date standards, job aids, and procedures
TECHNOLOGY
No turnkey products
Lack of features
Notes: Suggested Speaker Notes:
Significant gaps in quality management for 3D models fall into three categories:
People, Process, and Technology.
People: Undefined skillsets and lack of capacity
Technology: No turnkey products exist today and lack of features necessary to conduct reviews on 3D models
Process: Out of data standards, job aids, and procedures.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 10: Gaps: People
Reviewers may not always have skills for navigating and manipulating 3D models
Some modelers aren’t sure how to check their own work
Unsure how to keep a digital record of checks, especially when there are no issues to document
Undefined 3D modeling skillset required for model review tasks limits opportunity for training
Lack of training resources (e.g., manuals, videos)
PEOPLE
PROCESS
TECHNOLOGY
Notes: Suggested Speaker Notes
Gaps: People
Reviewer skill sets
Modeler skill sets
Record retention for digital checks
Lack of 3D modeling skill sets
Lack of resources
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 11: Gaps: Process
Formalized roles & responsibilities for reviewing digital files
Lack of standards for modeling and file management leading to inconsistent model structure
Lack of consistent and repeatable processes for checking digital files
Lack of job aids (e.g., checklists)
PEOPLE
PROCESS
TECHNOLOGY
Notes: Suggested Speaker Notes:
Gaps: Process
Roles and responsibilities for 3D model reviews
Lack of model management standards
Lack of standardized and repeatable processes
Lack of job aids to conduct processes
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 12: Gaps: Technology
Dynamic technology landscape with emerging products and features
Lack of robust tools for reviewing models
Lack of features to lock parametric models
Lack of features to facilitate reviews, in particular, routines to automate some types of geometric reviews
PEOPLE
PROCESS
TECHNOLOGY
Notes: Suggested Speaker Notes
Gaps: Technology
Emerging technology is still being developed
Lack of robust tools to fulfill all types of reviews
Lack of software features to “lock” elements once checked
Lack of automation for routine reviews
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 13: Opportunities
New ways to review a design
More detailed design intent
Direct Use of Design Data for Construction
Use of Design Data for Asset Management
Illustration: Figure 2 in NCHRP Research Report 1153
Notes: Suggested Speaker Notes
New opportunities and benefits for 3D model design reviews include
New ways to review a design
  Visualization of design in 3D
  Evaluating quantities directly from model elements
  Utilization of open data standards
More detailed design intent
  Better analysis of areas with complex geometry
  Visualize construction staging in 3D during design
  Communicate design intent to external stakeholders at public meetings
Direct use of design data for construction
  Deliver model based information in different formats such as
  Spreadsheets or tabular formats
  2D and 3D vector graphics in PDFs
  Open format exports
Use of design data for asset management
  Extraction of asset information in delivered 3D models for construction
  Application of property sets after construction
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 14: Challenges
Paperless Design Calculations
New Media for Executing Reviews
Auditable Quality Artifacts
New Media for Contract Documents
Illustration: Figure 3 in NCHRP Research Report 1153
Notes: Suggested Speaker Notes:
New challenges arise when utilizing model based approaches
Paperless design calculations
  New challenges with the accelerated usage and creation of calculations performed by software
  Timely validation of software or bespoke spreadsheets can be time-consuming
  Paperless design computations need to be archived so they are accessible over the life of the facility
New media for executing reviews
  Limited number of software packages that can view 3D models outside of the design authoring software.
  Reviewers need access to specific support configurations and software competencies
Auditable quality artifacts
  Quality artifacts need to be accessible to the extent for legal responsibilities for records retention
New media for contract documents
  Ability to archive and manage new media file types that may not be accessible for future audits
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 15: Guide Outline
Chapters
Introduction
Quality Management Concepts
Records Management
Model Reviews
Components of Review
Agency Considerations for Implementing this Guide
Appendices
Glossary of Terms
Model Elements Taxonomy
Review Documentation Property Set
Competencies
Review Procedures
Sample Quality Artifacts
Notes: Suggested Speaker Notes
The Guide outline includes chapters for
Introduction
Quality Management Concepts
Records Management
Model Reviews
Components of Review
Agency Considerations for Implementing this Guide
Appendices include:
A – Glossary of Terms
B – Model Elements Taxonomy
C – Review Documentation Property Set
D – Competencies
E – Review Procedures
F – Sample Quality Artifacts
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 16: Quality Management Concepts
Notes: Suggested Speaker Notes:
This next section will cover quality management concepts.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 17: International Standards
ISO 9000 series of standards for Quality Management Systems
ISO 9000 establishes quality management system concepts including the “Plan-Do-Check-Act” process
ISO 9001 establishes a certification framework for Quality Management Systems
A Quality Management System needs to be monitored for its effectiveness and routinely updated to reflect new practices or priorities.
Illustration: Figure 4 in NCHRP Research Report 1153
Notes: Definition of quality for 3D models is defined in the international standards in ISO 9000.
Plan Do Check Act cycle is a process to implement and continuously improve a quality management system.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 18: International Standards – ISO 19650
ISO 19650 is an Information Management standard for Building Information Modeling
Part 1 establishes concepts and principles
Part 2 provides requirements for project delivery
Part 4 provides requirements for information exchanges
Part 5 provides requirements for security
ISO 19650 is compatible with an ISO 9001-compliant Quality Management System
Notes: Suggested Speaker Notes:
ISO 19650 standard defines information management using BIM including
Principles and concepts
Requirements for project delivery
Requirements for operational phases of assets
Information exchanges
Security
Identifies key fundamental attributes, governance, and strategies that are significant for the quality management of 3D models and their application in design development
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 19: Approaches to Controlling Quality
Process Control
Controls how the product is produced to achieve repeatable and reliable outputs
Requires monitoring the inputs
Is applicable to design elements that follow a repeatable process that can be preconfigured
Identified issues can be corrected before design is complete
Monitoring can be automated
Product Control
Compares the finish product to the specifications to check compliance
Requires monitoring the outputs
Is applicable to all design elements
Identified issues lead to rework
Monitoring is labor intensive
Notes: Suggested Speaker Notes
Process control involves designing a repeatable process, monitoring the inputs, and managing the production process to achieve a predictable outcome
Product control involves thoroughly examining a finished product and comparing it to the specifications.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 20: Process Control Examples
Use a standard workspace configured for roadway design standards
  Roadway elements can only be created in a way that meets standards
Use a standard workspace configured for bridge design standards
  Designers can only select from a catalog of girders that match the standards
Use a MatLab model from a standard library that has been carefully tested
Notes: Suggested Speaker Notes:
Use a standard workspace configured for roadway design standards
  Roadway elements can only be created in a way that meets standards
Use a standard workspace configured for bridge design standards
  Designers can only select from a catalog of girders that match the standards
Use a MatLab model from a standard library that has been carefully tested
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 21: Quality Management System Notable Practices
Clearly defined QC roles
Standards for software, models & documentation
Design manuals or documented criteria
Checklists
Project quality plans
Quality audits
Certification
Notes: Suggested Speaker Notes
Notable quality management practices include:
Quality management manuals
Standards for software
Project quality plans
Standards for quality artifacts
Audits and certifications
Monitoring and feedback
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 22: Project Quality Management Process on a Project
The quality process is executed in parallel to the quality control process:
Start-up phase: develop a project quality plan.
Design phase: use resources identified in the plan at the milestones indicated in the plan to review the design and document evidence of the process. During the design phase, the resources are typically used in a five-step process, which includes auditing to verify that quality artifacts are complete and signed off.
Pre-letting phase: review quality documentation to verify the plan has been executed. Certify the design to attest that the quality management framework was properly implemented.
Illustration: Figure 5 in NCHRP Research Report 1153
Notes: Suggested Speaker Notes
The quality process is executed in parallel to the quality control process:
Start-up phase: develop a project quality plan.
Design phase: use resources identified in the plan at the milestones indicated in the plan to review the design and document evidence of the process. During the design phase, the resources are typically used in a five-step process, which includes auditing to verify that quality artifacts are complete and signed off.
Pre-letting phase: review quality documentation to verify the plan has been executed. Certify the design to attest that the quality management framework was properly implemented.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 23: 3D Model Reviews
Notes: Suggested Reader Notes
This next segment will cover 3D model reviews
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 24: Review Categories
Model Structure and Composition
3D Model Standards
3D Model Integrity
Design Compliance
Survey
Design Discipline (including Quantities)
Clash Detection and Spatial Coordination
Notes: Suggested Speaker Notes
Two categories of 3D Model reviews:
Model Structure and Composition
  Modeling standards review
  Model integrity review
Design Compliance
  Survey reviews
  Discipline design reviews
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 25: Structured Review Definitions
In the Chapter
Purpose and Outcomes
Scope of review for different types of deliverables
Required documents to execute the review
In the Appendices
Competencies to execute the review
Detailed Procedures
Sample quality artifacts
Notes: Suggested Speaker Notes:
The guide provides structures review definitions in Chapter 4 and the associated appendices.
The chapter defines the purpose and outcomes, scope of review for different types of deliverables, and required documents to execute the review
Information found in the appendices includes competencies to execute the review, detailed procedures, and sample quality artifacts.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 26: Model Structure and Composition Reviews
Addresses the use of modeling standards e.g., software configuration or workspace and naming conventions, model structure, templates or assemblies, element types, styles, and Level of Information Need (LOIN).
Introduces the model structure and composition review types:
  Modeling standards: compliance with the agency’s CADD/BIM/Model Development standards
  Model integrity: the modeling structure.
Notes: Suggested Speaker Notes:
This category of reviews focuses on how a model is constructed based on the agency modeling standards and structured content.
The model structure and composition reviews addresses the use of modeling standards e.g., software configuration or workspace and naming conventions, model structure, templates or assemblies, element types, styles, and Level of Information Need (LOIN).
Introduces the model structure and composition review types:
  Modeling standards: compliance with the agency’s CADD/BIM/Model Development standards
  Model integrity: the modeling structure.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 27: Design Compliance Reviews
Addresses the conformance of the model with the design and the conformance of the design with the applicable codes, standards, and technical criteria.
Introduces the three design compliance review types:
  Survey: compliance with agency geomatics or survey specifications for developing and delivering existing conditions models.
  Design Discipline: overall functionality of the design and compliance with project requirements for design standards, design intent and project milestone deliverables, constructability, quantities, and cost estimates
  Clash Detection & Spatial Coordination: analysis of each discipline model to evaluate the position of discipline specific model elements in relationship to each other as well as in relation to model elements from other disciplines.
Notes: Suggested Speaker Notes
This category of reviews focuses on confirming the model conforms to applicable design codes and standards.
Design Compliance Reviews addresses the conformance of the model with the design and the conformance of the design with the applicable codes, standards, and technical criteria
Introduces the three design compliance review types:
  Survey: compliance with agency geomatics or survey specifications for developing and delivering existing conditions models.
  Design Discipline: overall functionality of the design and compliance with project requirements for design standards, design intent and project milestone deliverables, constructability, quantities, and cost estimates
  Clash Detection & Spatial Coordination: analysis of each discipline model to evaluate the position of discipline specific model elements in relationship to each other as well as in relation to model elements from other disciplines.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 28: Roles and Responsibilities
Responsibilities of quality management roles include originator, reviewer, back checker, verifier, certifier, and auditor.
These responsibilities can be distributed across project roles depending on the project size and reviewer type such as:
Project Manager
Design Manager
Discipline Lead
CADD/BIM Manager
Discipline Model Manager
Model Authors
Quality Assurance Manager
Agencies can use Appendix C to correlate defined property sets that can be attributed to model files based on review fields for these responsibilities.
Notes: Responsibilities of quality management roles include originator, reviewer, back checker, verifier, certifier, and auditor.
These responsibilities can be distributed across project roles depending on the project size and reviewer type.
Agencies can use Appendix C to correlate defined property sets that can be attributed to model files based on review fields for these responsibilities.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 29: Quality Management Process for a Deliverable
During the initiate phase of the quality management process, a six-step review preparation process is needed.
The six step process includes
Step 1 – Identify the reviewers
Step 2 – Notify the reviewers of upcoming review
Step 3 – Thoroughly check the work and rectify any issues
Step 4 – Prepare the review artifacts and populate as appropriate
Step 5 – Transmit the package of files and documents
Step 6 – Notify the reviewers that files are ready for review
Review preparation emphasizes the need to check one’s own work before submitting the work for review.
Illustrations: Figure 8 in NCHRP Research Report 1153
Notes: Suggested Speaker Notes
During the initiate phase of the quality management process, a six-step review preparation process is needed.
The six step process includes
Step 1 – Identify the reviewers
Step 2 – Notify the reviewers of upcoming review
Step 3 – Thoroughly check the work and rectify any issues
Step 4 – Prepare the review artifacts and populate as appropriate
Step 5 – Transmit the package of files and documents
Step 6 – Notify the reviewers that files are ready for review
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 30: Quality Management Process for a Deliverable Continued Illustrations: Figure 7 in NCHRP Research Report 1153
During the check phase of the quality management process, a three-step review process is needed.
The review process consists of
Step 1 – Isolate the content in the model
Step 2 – Compare it to the standard
Step 3 – Document the check, and log any issues
The high-level procedure for Design Intent reviews is relatively simple, but in practice it requires two distinct skillsets:
Domain expertise to navigate the design standards, and
Modeling skills to open the file, isolate content, and view the properties.
Notes: Suggested Speaker Notes:
During the check phase of the quality management process, a three-step review process is needed.
The review process consists of
Step 1 – Isolate the content in the model
Step 2 – Compare it to the standard
Step 3 – Document the check, and log any issues
The high-level procedure for Design Intent reviews is relatively simple, but in practice it requires two distinct skillsets:
Domain expertise to navigate the design standards, and
Modeling skills to open the file, isolate content, and view the properties.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 31: Review Process and Preparation
4 key areas that need to be updated
Review Timeline with new review types
Preparing a Model for Review
Review Protocols
Standardizing Clash Routines
Section 4.5.3 provides guidance to agencies to establish their own review protocols. Appendix E provides an example set of review protocols.
Notes: Suggested Speaker Notes
The addition of 3D model-based design reviews affect the traditional quality management timeline
Examples of review types and when they are performed during the traditional review timeline is shown.
Section 4.5.3 provides guidance to agencies to establish their own review protocols. Appendix E provides an example set of review protocols.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 32: Competencies
Competencies included in Appendix D
CADD
Common Data Environment
Design
Appendix D contains a library of competencies organized in categories and sub-categories
Competencies can be used to develop and expand review types and develop customized training content for specific roles
Notes: Suggested Speaker Notes
Appendix D contains a library of competencies organize din categories and sub-categories.
The library covers three categories: CADD, Common Data Environment, and Design.
Each category has a group of sub-categories.
Where indicated, a competency has prerequisite or dependent competencies.
These are competencies that are required to execute the competency.
Project teams can use the competencies as criteria to screen potential reviewers.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 33: Review Procedures
Chapter 4 defined the scope of the review & review information needed for the review procedures
Review Initiation
Modeling Standards Review
Model Integrity Review
Survey – Geodetic
Survey – Topographic Features and 3D Surfaces
Survey – Land Boundaries & ROW
Discipline Design Review
Clash Detection and Spatial Coordination
Appendix E combines competencies and step by step review procedures
Core competencies for executing review
Review Procedure
Notes: Suggested Speaker Notes:
Chapter 4 defined the scope of the review & review information needed for the review procedures
The review procedures include:
Review Initiation
Modeling Standards Review
Model Integrity Review
Survey – Geodetic
Survey – Topographic Features and 3D Surfaces
Survey – Land Boundaries & ROW
Discipline Design Review
Clash Detection and Spatial Coordination
Appendix E combines competencies and step by step review procedures
The procedures assume a particular approach to agency standards and review documentation (e.g., using a MET).
Best practices include incorporating the review initiation process into each procedure and understanding process and product controls when choosing software to implement these procedures.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 34: Setting Up for Success
Notes: Suggested Speaker Notes:
This next section will cover setting up your agency for success
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 35: Components of Successful Review Processes
A standard approach to model development provides the design team and reviewers with a structured framework for planning, creating, and verifying model-based deliverables. Chapter 5 covers:
Information Modeling Standards
Describes the role of Level of Development (LOD) / Level of Information Need (LOIN)
Common Data Environment
Naming Conventions
Software Configuration Development and Management
Model Management Tools
A sample naming convention based on ISO 19650-2 can be used to develop an agency’s standard
Illustration: Figure 10 in NCHRP Research Report 1153
Notes: Suggested Speaker Notes:
A successful review PROCESS requires a well-organized model development environment and workflow.
Chapter 5 of the guide elaborates on specific model environment components that agencies should establish and implement for a robust quality management process.
This include:
Information Modeling Standards which describes the role of Level of Development and Level of Information Need
Common Data Environment
Naming Conventions
Software Configuration Development and Management
Model Management Tools
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 36: Information Modeling Standards
Information Modeling Standards specify the level of detail and information for a specific purpose.
  Geospatial positional accuracy and point density requirements for base survey mapping
Appendix E for Survey Review Procedures
  Object-based design elements organized following a specific Model Element Table
See Appendix B for the Model Elements Taxonomy
  Level of detail and information specified by milestone deliverable
  CAD standards for software configuration
Notes: Suggested Speaker Notes:
Information modeling standards are the basis for the modeling standards and model integrity reviews.
Clearly defined naming conventions, model content, and element information yield finished products that are consistent and predictable.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 37: Common Data Environment
CDE - a collaborative space for production of federated models that bring together information containers from multiple sources and parties
Processes for approval and records management
  Notifications and alerts plus audit trail.
  Workflow engines to automate review and approval processes.
  Configure workflows to project methods and procedures.
Protects the security and quality of information throughout production, review, and delivery.
  Permissions controls (gated CDE workflows)
Information Containers
Work in Progress
Shared
Published
Archived
Notes: Suggested Speaker Notes:
Considerations for a well-configured CDE that fully supports review protocols include:
Approval and verification workflows configurable to project methods and procedures.
Notifications and alerts that aid collaborative workflows and audit trail.
Permissions controls that are customizable and provide gated CDE workflows.
Workflow engines to automate review and approval processes.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 38: Software Configurations
Specifications for software configuration
Requirements for software packages and versions for the development of models (if applicable)
Sections 5.2.3 & 5.2.4 provide guidance to agencies on naming conventions, drawing symbology (e.g., points, lines, annotation), 2D and 3D object libraries, etc.
Customized repeatable processes and workflows using modeling standards.
Consistency with design and modeling standards between users
Ability to implement process control and checks against the configuration.
Notes: Suggested Speaker Notes:
Advantages of implementing an agency software configuration include:
Defining customized repeatable processes and workflows using modeling standards.
Promoting consistency with design and modeling standards between users.
Providing the ability to implement process control and checks against the configuration.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 39: Model Management Tools
Model Content Documentation tells reviewers what is in the model, saving time and providing a resource to compare with agency standards.
BIM Execution Plan (BEP)
  File List and Types
  Model Uses
  Review tracking
Provided to reviewers for their reference to understand the project needs and implementation process for model generation.
Model Element Table (MET)
  Standardize for consistency
  Object information
    What’s Included
    LOD/LOIN
Agencies can incorporate a MET into a formal review process by maintaining a scalable template for different project types.
Notes: Suggested Speaker Notes:
Model Content Documentation tells reviewers what is in the model, saving time and providing a resource to compare with agency standards.
BIM Execution Plan (BEP)
  File List and Types
  Model Uses
  Review tracking
  Provided to reviewers for their reference to understand the project needs and implementation process for model generation.
Model Element Table (MET)
  Standardize for consistency
  Object information
    What’s Included
    LOD/LOIN
  Agencies can incorporate a MET into a formal review process by maintaining a scalable template for different project types.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 40: Review Tools and Job Aids
Review tools and job aids that form the primary tool for executing reviews, i.e., include:
Checklists
Section 5.3.1 provides guidance to agencies to establish their own. Appendix F provides example checklists.
Generating Reports
Automated Tools
Software Applications for 3D Model Reviews
Each section provides details on the types or categories of tool and job aid and provides guidance to agencies on implementing these core elements of how the 3D model reviews are executed as part of an agency’s standards and policies.
Notes: Suggested Speaker Notes:
Reviewers need a sound process to verify a model contains the design information necessary for the contractor and meets design criteria and calculations
Review tools and job aids that form the primary tool for executing reviews, i.e., include:
Checklists
Generating Reports
Automated Tools
Software Applications for 3D Model Reviews
Each section provides details on the types or categories of tool and job aid and provides guidance to agencies on implementing these core elements of how the 3D model reviews are executed as part of an agency’s standards and policies.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 41: Sample Quality Artifacts
Notes: Suggested Speaker Notes:
This next section will cover sample quality artifacts
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 42: Sample Quality Artifacts
The sample quality artifacts listed in Appendix F are created and formatted from industry examples and project experience. They include:
  Checklists
  Report Exports
  Model Element Tables
  Review Comment Organization
Demonstration of the Appendix F workbook
Notes: Suggested Speaker Notes
Introduce the sample quality artifacts included in Appendix F.
Presenter can switch screen sharing to the NCHRP Project 10-113, Appendix F Addendum: Review Checklist spreadsheet.
Describe the Key Concepts of each tab as outlined in Appendix F.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 43: Agency Considerations
For Implementing This Guide
Notes: Suggested Speaker Notes:
This next section will cover agency considerations for implementing this guide
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 44: Introduction
PEOPLE
Change Management and Workforce Development
Establishing roles and responsibilities
Defining competencies for model-based design reviews
Setting up committees, working groups, and collaborations with peer agencies
PROCESS
Planning Changes to the Quality Process
Reviewing and updating current quality management policies and procedures
Implementing agency-specific standards, job aids, and quality artifacts
TECHNOLOGY
Technology: Current Functionality and Future Developments
Evaluating technology relevant to the quality management of 3D models
Partnering with software vendors to develop short and long-term strategies for successful implementation
Notes: Suggested Speaker Notes:
Suggestions for implementing this guide are organized using the People-Process-Technology framework.
This framework balances competing needs and gaps against how guidelines fit within an element
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 45: People: Change Management & Workforce Development
While the roles and responsibilities of design team members are not dramatically changing, the competencies required, and methods used to perform and document reviews are different for a model-based environment.
This section describes guidelines for short and long-term activities related to upskilling the current workforce, including:
Agency Guidelines
Coordination, Collaboration and Partnerships
Training Content and Delivery
Appendix D provides 3D modeling competencies. Appendix E lists the competencies required for each of the five review types.
Notes: Suggested Speaker Notes:
It is important for agencies to review current job descriptions to identify gaps in required and preferred qualifications.
Based on this analysis, agencies can develop and deploy an education and training plan to upskill current and future workforce.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 46: Process: Planning Changes to the Quality Process
This section provides guidelines for agencies updating the quality management process. Three key areas are identified that may need to be evaluated and updated.
QA documentation requirements
Chapter 3 provides guidelines for management of digital records. Appendix C offers a collection of review documentation property sets.
QC standards and procedures
Items to consider during evaluation include updating or establishing roles and responsibilities, introduce new documentation, update standards and criteria for review processes, and create or update modeling standards.
Review tools and job aids
Notes: Suggested Speaker Notes:
While the five step quality management process remains unchanged, the three key areas need to be evaluated and updated.
QA documentation requirements
QC standards and procedures
Review tools and job aids
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 47: Review Tools and Job Aids
This section describes items to consider while evaluating software and updating job aids.
Assess current CDE
Chapter 5 has general guidelines. ISO 19650-1 defines functional requirements for procurement of a CDE.
Acquire model based review tools
Working with vendors on configurations
Updating checklists or other job aids
Sample checklists are provided in Appendix F for reference.
Notes: Suggested Speaker Notes:
Items to consider during the evaluation of acquiring new tools and job aids include:
Assess the functional requirements of current or future CDE
Acquiring a model based design review software for non-CADD users
Working with software vendors to set up or evaluate software configurations
Developing or updating checklists for model based quality management
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 48: Process: Implementing Standards and Process Control
Section 6.3.2 and 6.3.3 provide guidance on defining and implementing processes for:
Establishing Information Modeling Standards
Leveraging modeling software configuration to create a consistent and repeatable model-based design processes
Creating on boarding training procedures
Don’t forget!
Product Control vs Process Control
Notes: Suggested Speaker Notes:
The process for implementing standards and process control is explained in section 6.3.2 and 6.3.3 in the guide.
These sections provide guidance on defining and implementing processes for:
Establishing Information Modeling Standards
Leveraging modeling software configuration to create a consistent and repeatable model-based design processes
Creating on boarding training procedures
It is important to note that a well-defined process control framework is likely to result in a reduced numbers of product control
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 49: Technology: Current Functionality and Ongoing Developments
This section provides a summary of current software functionality and gaps, existing automation tools and the role of open data standards
Existing automation tools can be broken into three types
CADD Standards Compliance Checks
Design Code Compliance Checks
3D Design Review and Clash Detection Checks
Human reviewers are essential for checking nuances of design, but software can provide automated checks of design standards and changes between milestone reviews. It is important for agencies define their standards and functional requirements based on performance outcomes rather than prescriptive methods.
Notes: Suggested Speaker Notes:
This section of the guide summarizes current software functionality and gaps.
It offers guidelines for working with software vendors and industry to improve functionality and advance automation of tools for reviewing model integrity.
Along with verifying model-based design and information requirements.
Human reviewers are essential for checking nuances of design, but software can provide automated checks of design standards and changes between milestone reviews. It is important for agencies define their standards and functional requirements based on performance outcomes rather than prescriptive methods.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 50: The Role of Open Data Standards
Current development for the deployment and adoption of open data standards is being developed through two AASHTO Pooled Funds:
TPF-5(372) – Building Information Modeling (BIM) for Bridges and Structures
TPF-5(523) - Building Information Modeling (BIM) for Bridges and Structures – Phase II
Open data standards rely on the IFC schema that is used to reference model elements within a design to the IFC data structure.
In relation to quality management:
buildingSMART IFC File Validation Service
Information Delivery Specification (IDS)
Notes: Suggested Speaker Notes
Current development for the deployment and adoption of open data standards is being developed through two AASHTO Pooled Funds
  TPF-5(372) – BIM for Bridges and Structures
  TPF-5(523) – BIM for Bridges and Structures Phase II
Open data standards rely on the IFC schema that is used to reference model elements within a design to the IFC data structure.
Two aspects that are in relation to quality management include:
  buildingSMART IFC File Validation Service
  Information Delivery Specification (IDS)
Agencies should stay informed about the development of these standards as this is a solution for keeping proprietary file types accessible into the future.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 51: Summary
Research objective was to develop a guide that can serve as a national industry reference for quality assurance with 3D model-based project delivery
NCHRP Project 10-113, “Quality Management for 3D Model-Based Project Development and Delivery”
  Deliverables include:
  Guide
  Conduct of Research Report
  Implementation Plan
  Outreach Materials: Webinar
The guide provides a consistent, repeatable, reproducible, and traceable quality management process that is equal to or better than existing paper-based processes.
Notes: Suggested Speaker Notes
Let’s summarize today’s presentation on NCHRP Project 10-113, Quality Management for 3D Model Based Project Development & Delivery
The research objective was to develop a guide that can serve as a national industry reference for quality assurance with 3D model-based project delivery
The deliverables for the project include:
  The Guide
  The Conduct of Research Report
  An Implementation Plan
  Outreach materials – which includes this webinar presentation
The guide provides a consistent, repeatable, reproducible, and traceable quality management process that is equal to or better than existing paper-based processes.
CLICK NEXT TO ADVANCE TO NEXT SLIDE

## Slide 52: Questions
Notes: Suggested Speaker Notes
I will now open the floor for questions.
(If questions are done through a virtual chat or Q&A session, read each question prior to answer it)
Thank you for attending this presentation of the NCHRP Project 10-113, Quality Management for 3D Model-Based Project Development and Delivery, Guide Overview
END PRESENTATION

## Slide 53: Disclaimer
This presentation was created as part of NCHRP Project 10-113, “Quality Management for 3D Model-Based Project Development and Delivery” along with NCHRP Research Report 1153: Digital Model–Based Project Development and Delivery: A Guide for Quality Management.
The National Cooperative Highway Research Program (NCHRP) is sponsored by the individual state departments of transportation of the American Association of State Highway and Transportation Officials. NCHRP is administered by the Transportation Research Board (TRB), part of the National Academies of Sciences, Engineering, and Medicine, under a cooperative agreement with the Federal Highway Administration (FHWA). This material is based upon work supported by the FHWA under Agreement No. 693JJ32350025. Any opinions, findings, and conclusions or recommendations expressed or implied in resulting research products are those of the individuals and organizations who performed the research and are not necessarily those of TRB; the National Academies of Sciences, Engineering, and Medicine; the FHWA; or NCHRP sponsors.